INTRODUCTION
Based on findings from first School Improvement Place for Literacy the following areas were identified;

SUMMARY OF MAIN STRENGTHS
- Uptake at Higher Level in Leaving Certificate is very high, needs to be maintained.
- DEAR ran very well, needs to be maintained.
- Willingness of staff to try new teaching approaches.
- Willingness of staff to engage positively with literacy strategies.
- Many of the classrooms have their own libraries.
- Students have a positive disposition towards reading.

SUMMARY OF MAIN AREAS PRIORITISED FOR IMPROVEMENT
Focus needs to be put on initiatives in areas such as oracy, group work and presentations to a group.
- Those reading for pleasure didn’t reach desired levels.
- Provision of reading material and reading suggestions needs to be highlighted.
- Parents/Guardians need to be more informed on strategies and initiatives that are in place.
- Students digital literacy is poor, strategies need to be put in place to help.
Target No.1 Reading for Pleasure
Improvement Targets	Required Actions	Person(s) Responsible	Timeframe for Actions	Success Criteria/Measurable Outcomes	Review Date
To increase the number of students reading more than two non-syllabus books in their second year in secondary school by 5% in Year 1 (2016-17), 4% in Year 2 (2017-18) and 3% in Year 3 (2018-19).	1. All classes to have DEAR Programme-Twenty minute reading slot in one class each week (class/time rotated throughout the school year) / 2. Promotion of reading board among staff and students. / 3. Students to be surveyed on their interests. Books to be purchased from the literacy budget. Recommended books to be listed and given to students and put on website. / 4. Library classes for all First Year English classes and in Second Year until Christmas / 5. All departments to develop subject libraries. / 6. Book in the Bag for all 1st, 2nd, 3rd and Transition Year classes / 7. First Year students encouraged to join Wexford library.	1. All teachers ,Senior management to do timetable and announce DEAR on the intercom. / 2. Literacy link teacher, all teachers. TY students. / 3. First Year Induction Team and English teachers. / 4. English Dept. / 5. All subject Dept. / 6. All teachers covering classes. / 7. Literacy link teacher/First year English teachers	1.DEAR time-20mins per week every week from September . / 2. Staff Meetings and weekly in English classes. / 3. Each Induction Day and throughout the year. / 4. Every week. / 5. Throughout the year, subject meetings.. / 6. Every day / 7. Throughout year	Increase in the number of students reading more than two books –monitored by survey to be carried out each year. / Increase in the number of postings on the school reading boards.	May 2017 / May 2018 / May 2019
	8. Book reviews to be carried out by each student. Some will be presented orally/visually. / Links with Target 4.	8. English Dept. with all First, Second and Transition Year classes.	8. Throughout year	8.. Students will have completed at least three books reviews per year.
	9. Updates and feedback to parents through parent/teacher meetings/blog/newsletters/information meetings. / 10. Feedback from staff.	9. All teachers at PTM/information Nights. / School blogger/senior management. / 10. Literacy team.	9. Parent/teacher meetings and information Nights. / Blog on a regular basis. / Newsletter in each term / 10. Survey in May 2016/2017/2018.	9.. Parental survey indicating positive attitude to initiatives. / .

Target No. 3 Improving students’ oracy skills
Improvement Targets	Required Actions	Person(s) Responsible	Timeframe for Actions	Success Criteria/Measurable Outcomes
Decrease the number of students who do not like to speak in front of their class peers by 10% in Year 1, 10% in Year 2 / and 5% in Year 3.	1. CPD for staff on oral language strategies including pair/group work and agreed checklists for oral presentations. / 2.Oral presentation to become part of the assessment of all First year students in every subject	1.Literacy team. / 2. All First Year teachers	1.Staff Meetings / 2.Christmas and May exams	1-2.Increase in the number of teachers using pair/group work and oral presentations as part of their teaching methodologies in First Year classes (Documented in Subject Dept. minutes/ Staff survey).
	3.All First Years to attend Speech and Drama workshop with a specific focus on oral presentations	3.Senior Management/English Dept.	One class a week for 4 – 6 weeks in 1st year.	3.Students more willing to participate in pair/group work and class discussions (Staff and student survey).
	4.Guide to be provided to parents to help them support their child through the oracy programme	4.Senior management and literacy link teacher		4.Increase awareness among parents as to the merits of oral literacy development (Parental survey).

Target No. 4 Digital Oracy
Improvement Targets	Required Actions	Person(s) Responsible	Timeframe for Actions	Success Criteria/Measurable Outcomes	Review Date
To increase the number of students who are competent with basic computer skills. / - Improve ability on Word in Year 1 (2016/17) / -Improve ability with PowerPoint in Year 2 (2017/18) / -Improve ability with Publisher in Year 3 (2018/19) / 1 class group from 1st years 2016/17 to follow programme, / 2 class groups from 1st years 2017/2018 to follow programme / and 3 class groups from 1st years 2018/2019 to follow programme	1. Survey class as to how competent they are in desired area. / 2. Provision of one class a week for 4 weeks / 3. All students to be provided with memory stick to save work on. / 4. Completion of a presentation in each year on programme being focused on. / 5. Each subject to have at least one homework assignment to be completed digitally in course of year.	1. English teacher. / 2. Senior Management / 3. Senior Management / 4 Computer teacher / 5. Subject teachers	1. Survey with group on relevant topic at start of year. / 2. 4 weeks / 3. During Stay Strong week / 4. By end of computer classes / 5. By end of year.	Increase in the number of students competent in using Office programmes. -survey to be carried out in September and again in May / Piece of work reviewed by teachers.	May 2017 / May 2018 / May 2019
	8. Internet Safety Awareness	8. All staff, management and speakers.	8. During Stay Strong Week